## original plan
Planning
Project:
Project group:			Group 20			Date:		2010-09-14					Reviewed:
Customer:			Syed Asad Alam			Version:		0,1
Course:			TSTE12			Author:
ACTIVITIES					TIME	WHO	TIME PLAN (week number)
No	Description				Hours	Initials	36	37	38	39	40	41	42	43
1	Requirement specification				35	All	30	5					35
2	Project plan				20	All		20					20
3	Design specification				40	All		40					40
4	Time plan				8	All		8					8
	Final report and presentation				40	All					20	20	E					40
5	VGA controller				60				30	30			X					60
6	Audio controller				50				30	20			A					50
7	Keyboard controller				20				20				M					20
8	Digital oscilloscope				70					15	35	20	-					70
9	Equalizer				50					20	20	10	P					50
10	Meetings				7	All	1	1	1	1	1	1	E	1					7
11	Back-up time				80	All			10	20	20	20	R	10					80
12					I					0
13					O					0
14					D					0
15					0
16					0
17					0
18					0
19	Deadlines					0
20	Requirement specification					Tue					0
21	Project plan, design specification and time plan					Ons					0
22	Final report and presentation					Fri					0
23					0
24	Milestone					0
25	All priority 1 demands finished					Fri					0
26					0
	Total number of hours				480		31	74	91	106	96	71	0	11	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	480

## Summing of time
SUMMING OF TIME
Project:			0
Project group:			Group 20			Date:		2010-09-14					Reviewed:
Customer:			Syed Asad Alam			Version:		0,1
Course:			TSTE12			Author:
RESOURCE					USED TIME (per week)
	Name					36	37	38	39	40	41	42	43	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	Su
	Jimmie Lahti					0
	Johan Hellman					0
	Henrik Andersson					0
	Gustav Wallin					0
	Joakim Tosteberg					0
	Erik Frej					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
	Total number of hours:					0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0